## DC
Tamplate Information
Document Name : |  | Project Monthly Report Tamplate
Document Ref. No. : |  | ADM - MIA - 4.1 - F - 04
Version : |  | 4
Issue Date : |  | 2021-05-24
Document Owner : |  | Abu Dhabi Municipality - Infrasctructure and Municipal Assests Sector
User Instruction :
1 | All data in all sheets are required
2 | Summary dashboard is reading automatically from the data already provided in other sheets
3 | Please enter Dates and Numbers carefully in correct formats, improper formats may affecte the auto calculations in the document
4 | The range for Auto Calculations in each logsheet is 200 rows, for logs containing data exceed 200 rows formulas should be amended
5 | Please be aware about any undesired inputs in the range of calculation in each log
6 | All Contracts values and cash flow and payments gross amount exclding VAT
7 |  | Formats for fields should be filled manually by user
8 |  | Formats for fields should be filled manually and HAVE CRITICAL IMPACT ON THE AUTO CALCULATION
9 |  | To be filled by ADM Staff
10 |  | Formats for fields calculated automatically
11 |  | Formats for Columns in log sheet where fields calculated automatically
Content Description :
Form | Sheet Name | Sheet Description
00 | DC | Information about this template
01 | Covering Page | Project Name and Detailes (Project name and project number will appear in all other pages based on this sheet value)
02 | Summary | Dashboard contains key informations and summary about project status as of the report Cut-off date
03 | Acheivements | Brief about major Achievements in the project during this month
04 | Schedule | Brief about major activities in whole project Schedule
05 | Commercial Status C | Payments and Contractual information for contractor
06 | Commercial Status E | Payments and Contractual information for consultant
07 | Quality Status | Main statistics about quality items
08 | Project Issues | Major issues in the project
09 | Critical Submitals | Critical submittals which effect on project schedule
10 | Risk Register | Project risk register with assessment and mitigation plans
11 | CashFlow & Progress | Brief about Project Cash Flow and Progress
12 | Resources | Project resources status
13 | KPIs | Status of Main KPIs in the project
14 | Progress Photos | Photos for project activities and achievements
15 | Claims Status | Claims Register with all information about Claims
16 | Claims Details | Claims events with all information about events
17 | VOs Status | Variations Orders with all information about Vos
18 | Recap Status | Recap calculations for project progress
19 | HSE Status | Summary Statistics for Health and Safety and Environmental Issues in the project
20 | HSE Training | HSE Training Register for Project
21 | HSE Incidents | HSE Incidents Register for Project
22 | HSE NCR's Log | HSE NCR's status report for Project
Project Risk Management Methodology
1 | Risk Matrix
مصفوفة المخاطر Risk Matrix |  |  | Risk Probability تقييم الاحتمالية
|  |  | مؤكد Very High 5 | غالبا High 4 | محتمل Medium 3 | ضعيف Low 2 | ضعيف جدأ Very Low 1
Risk Impact تقييم الأثر |  | مرتفع جدا Very High 5 | 25 عالي جداً Very High | 20 عالي جداً Very High | 15 عالي High | 10 عالي High | 5 متوسط Medium
|  | مرتفع High 4 | 20 عالي جداً Very High | 16 عالي جداً Very High | 12 عالي High | 8 متوسط Medium | 4 منخفض Low
|  | متوسط Medium 3 | 15 عالي High | 12 عالي High | 9 عالي High | 6 متوسط Medium | 3 منخفض Low
|  | منخفض Low 2 | 10 عالي High | 8 متوسط Medium | 6 متوسط Medium | 4 منخفض Low | 2 منخفض جداً Very Low
|  | منخفض جدأ Very Low 1 | 5 متوسط Medium | 4 منخفض Low | 3 منخفض Low | 2 منخفض جداً Very Low | 1 منخفض جداً Very Low
2 | Risk Assessment Criteria
الاحتمالية Probability
معايير تقييم الاحتمالية Probability Criteria |  | مؤكد Very High |  | غالبا High |  | محتمل Medium |  | ضئيل Low | ضئيل جدأ Very Low
|  | حدث الخطر سابقاً في المشروع الحالي أكثر من مرة ويحصل عادة في مشاريع مشابهة Risk has Occurred Previously Many Times During This Project, And it is Occurred Usually in Other Similar Projects |  | حدث الخطر سابقاً في المشروع الحالي ويحصل عادة في مشاريع مشابهة Risk has Occurred Previously During This Project, And it is Occurred Usually in Other Similar Projects |  | لم يحدث الخطر في المشروع الحالي ولكن يحصل عادة في مشاريع مشابهة Risk has Not Occurred Previously During This Project, But it is Occurred Usually in Other Similar Projects |  | لم يحدث الخطر في المشروع الحالي ولكن حصل نادراً في مشاريع مشابهة Risk has Not Occurred Previously During This Project, But it is Occurred Sometimes in Other Similar Projects | لم يحدث الخطر في المشروع الحالي ولا في أي من المشاريع المشابهة Risk Never Occurred Previously During This Project or Other Semilar Projects
نوع الخطر Risk Type |  | Risk Impact تقييم الأثر
|  | عالي جداً Very High |  | عالي High |  | متوسط Medium |  | ضعيف Low | ضعيف جداً Very Low
مالي Financial |  | يؤدي الخطر إلى الإنحراف عن الميزانية المخططة للمشروع بنسبة تزيد عن 30% Risk could lead to deviation from planned budget more than 30% |  | يؤدي الخطر إلى الإنحراف عن الميزانية المخططة للمشروع بنسبة بين 20% - 30% Risk could lead to deviation from planned budget between 20% - 30% |  | يؤدي الخطر إلى الإنحراف عن الميزانية المخططة للمشروع بنسبة بين 15% - 20% Risk could lead to deviation from planned budget between 15% - 20% |  | يؤدي الخطر إلى الإنحراف عن الميزانية المخططة للمشروع بنسبة بين 10% - 15% Risk could lead to deviation from planned budget between 10% - 15% | يؤدي الخطر إلى الإنحراف عن الميزانية المخططة للمشروع بنسبة تقل عن 10% Risk could lead to deviation from planned budget less than 10%
زمني Schidual |  | يؤدي الخطر إلى الإنحراف عن الجدول الزمني المعتمد للمشروع بنسبة تزيد عن 30% Risk could lead to deviation from planned schedule more than 30% |  | يؤدي الخطر إلى الإنحراف عن الجدول الزمني المعتمد للمشروع بنسبة بين 20% - 30% Risk could lead to deviation from planned schedule between 20% - 30% |  | يؤدي الخطر إلى الإنحراف عن الجدول الزمني المعتمد للمشروع بنسبة بين 15% - 20% Risk could lead to deviation from planned schedule between 15% - 20% |  | يؤدي الخطر إلى الإنحراف عن الجدول الزمني المعتمد للمشروع بنسبة بين 10% - 15% Risk could lead to deviation from planned schedule between 10% - 15% | يؤدي الخطر إلى الإنحراف عن الجدول الزمني المعتمد للمشروع بنسبة تقل عن 10% Risk could lead to deviation from planned schedule less than 10%
جودة Quality |  | مخاطر تمنع كلياً تحقيق الأهداف والمخرجات الرئيسية للمشروع Risks prevent completely achieving the main goals / Outcomes of the project |  | مخاطر تمنع جزئياً تحقيق الأهداف والمخرجات الرئيسية للمشروع . Risks prevent partially achieving the main goals / Outcomes of the project |  | مخاطر تؤثر على تحقيق الأهداف والمخرجات الرئيسية للمشروع Risks affect achieving the main goals / Outcomes of the project |  | مخاطر تؤثر بشكل بسيط على تحقيق الأهداف والمخرجات الرئيسية للمشروع Risks slightly affect achieving the main goals / Outcomes of the project | مخاطر تؤثر على تحقيق الأهداف والمخرجات الثانوية للمشروع Risks affect achieving subsidiary goals / Outcomes of the project
|  | مخاطر تؤدي إلى عدم الالتزامات بالمواصفات الفنية بشكل كامل لكافة الأصول Risks lead to completely non-compliance with the technical specifications for all assets |  | مخاطر تؤدي إلى عدم الالتزامات بالمواصفات الفنية بشكل جزئي لكافة الأصول Risks lead to partially non-compliance with the technical specifications for all assets |  | مخاطر تؤدي إلى عدم الالتزامات بالمواصفات الفنية بشكل كامل لبعض الأصول Risks lead to completely non-compliance with the technical specifications for some assets |  | مخاطر تؤدي إلى عدم الالتزامات بالمواصفات الفنية بشكل جزئي لبعض الأصول Risks lead to partially non-compliance with the technical specifications for some assets | مخاطر تؤدي إلى عدم الالتزامات بالمواصفات الفنية للأصول بشكل طفيف جداً لبعض الأصول Risks lead to slightly non-compliance with the technical specifications of some assets
|  | مخاطر إلى فقدان كامل لبيانات ومستندات المشروع Risks lead to completely missing in project information or documents |  | مخاطر إلى فقدان كبير في بيانات ومستندات المشروع Risks lead to major missing in project information or documents |  | مخاطر إلى فقدان بسيط في بيانات ومستندات المشروع Risks lead to slightly missing in project information or documents |  | مخاطر تؤثر على دقة بيانات ومستندات المشروع Risks affect on accurecy of project information or documents | مخاطر تؤثر بشكل بسيط على دقة بيانات ومستندات المشروع Risks affect slightly on accurecy of project information or documents
|  | الخطر يؤثر على سمعة البلدية بشكل كبير Risks will have Major impact on ADM reputation |  | الخطر يؤثر على سمعة البلدية بشكل متوسط Risks will have medium impact on ADM reputation |  | الخطر يؤثر على سمعة البلدية بشكل مؤثر Risks will have effective impact on ADM reputation |  | الخطر يؤثر على سمعة البلدية بشكل طفيف Risks will have slight impact on ADM reputation | الخطر يؤثر على سمعة البلدية بشكل طفيف جدا Risks will have very slight impact on ADM reputation
تعاقدي / قانوني Contractual / Legal |  | مخاطر قد تؤدي إلى مخالفة كبيرة للقوانين والتشريعات Risks could lead to Major non-compliance for lows and legistlations |  | مخاطر قد تؤدي إلى مخالفة جزئية للقوانين والتشريعات Risks could lead to minor non-compliance for lows and legistlations |  | مخاطر قد تؤدي إلى عدم الالتزام بالشروط التعاقدية والالتزامات Risks could lead to non-compliance for Contracts and Contractual Commitments |  | مخاطر قد تؤدي إلى مطالبات تعاقدية كبيرة Risks could lead to major contractual claims | مخاطر قد تؤدي إلى مطالبات تعاقدية بسيطة Risks could lead to minor contractual claims
صحة وسلامة وبيئة HSE |  | مخاطر قد تؤدي إلى عدم التزام كامل بمتطلبات الصحة والسلامة والبيئة Risks could lead to major non-compliance for HSE Requirements |  | مخاطر قد تؤدي إلى عدم التزام جزئي بمتطلبات الصحة والسلامة والبيئة Risks could lead to minor non-compliance for HSE Requirements |  | مخاطر قد تؤدي إلى عدم التزام مؤثر بمتطلبات الصحة والسلامة والبيئة Risks could lead to effective non-compliance for HSE Requirements |  | مخاطر قد تؤدي إلى عدم التزام طفيف بمتطلبات الصحة والسلامة والبيئة Risks could lead to slight non-compliance for HSE Requirements | مخاطر قد تؤدي إلى عدم التزام طفيف جداً بمتطلبات الصحة والسلامة والبيئة Risks could lead to very slight non-compliance for HSE Requirements
3 | Risk Control
تقييم الخطر Risk Evaluation |  | مرتفع جدا Very High | مرتفع High | متوسط Medium | منخفض Low | منخفض جدا Very Low
|  | 16-25 | 9-15 | 5-8 | 3-4 | 1-2
الإجراء المطلوب Actions Required |  | يتطلب وضع خطة للتحكم وخفض المخاطر Risk Metigation Plan is Required (Corrective Action, Preventive Action, Control Action) |  |  | المراقبة والمتابعة Monitoring (No Action Required)
CPI Speedometer
|  |  |  | Gauge | Indicator
|  |  | CPI < 80% | 65% | 94.41% | CPI
|  |  | CPI 80% to 90% | 5% | 0% | CPI Min
|  |  | CPI 90% to 110% | 15% | 360% | CPI Max
|  |  | CPI > 110% | 95%
|  |  | CPI > 110% | 180%
SPI Speedometer
|  |  |  | Gauge | Indicator
|  |  | SPI < 80% | 65% | 70% | SPI
|  |  | SPI 80% to 90% | 5% | 0% | SPI Min
|  |  | SPI 90% to 110% | 15% | 360% | SPI Max
|  |  | SPI > 110% | 95%
|  |  | SPI > 110% | 180%

## Covering Page
Project Monthly Progress Report
| Project Title : | Project X
| Project DOF No. | xxx - xxxxxxx- xx
| Project Stage : | Initiation
| Consultatnt Name | Text here
| Contract Number : | Text here
| Report Number : | Text here |  | Revision No | 1.0
| Report Data Date : | 2021-12-25
| Submission Date : | 2021-01-01
| Prepared By | Name : | Text Here
|  | Position : | Text Here
Signature :
| Approved By | Name : | Text Here
|  | Position : | Text Here
Signature :
Note on B4: This title will appear in all sheets
Note on B14: Auto Progress Caculations will be based on this value

## Summary
Project Name |  | Project X | [30 empty] | Report Date |  | 2021-12-25 |  |  | R1.0
Project Description | [19 empty] | Project Information | [8 empty] | Project Location
Text Here | [19 empty] | Project Category |  |  |  | : | Roads
[20 empty] | Region |  |  |  | : | Mainland
[20 empty] | Location |  |  |  | : | E-13
[20 empty] | Roads Lane Length |  |  |  | : | 2000 |  | Lane Km
[20 empty] | Parks Area |  |  |  | : | 5000
Project Components | [19 empty] | No. of Plots |  |  |  | : | 200
Text Here | [9 empty] | Project Management |  | : | ADM | [6 empty] | Start Date |  |  |  | : | 2020-01-01
[10 empty] | Division |  | : | [7 empty] | End Date |  |  |  | : | 2021-12-31
[10 empty] | Project Manager |  | : | [7 empty] | Project Duration |  |  |  | : | 731 |  |  | Days
[20 empty] | Project Value |  |  |  | : | 100000000 |  |  | DHs
[20 empty] | Project Type |  |  |  | : | Design_Build
[20 empty] | Project Stage |  |  |  | : | Construction
Engineer Infromation | [10 empty] | Contractor Infromation | [17 empty] | Project Performance
Consultant Name | : | Text Here | [8 empty] | Contractor Name |  |  | : | Text Here
Contract Number | : | abc-3512-4521 | [8 empty] | Contract Number |  |  | : | abc-3512-4521 |  |  | Cost & Budget | [10 empty] | Budget Performance | [6 empty] | CEI
[5 empty] | Cost & Budget | [12 empty] | Contract Value |  |  |  |  | : | 22000000 |  |  | DHs |  | Budget This Year | : | By ADM |  |  | Dhs
Schedule |  |  |  |  | Contract Value | : | 22000000 |  | DHs |  | Schedule | [6 empty] | Approved Changes |  |  |  |  | : | 3000000 |  |  | DHs |  | Planned To Date | : | 0 |  |  | Dhs |  | By ADM
Commenc. Date | : | 2020-04-01 |  |  | Approved Changes | : | 11000 |  | DHs |  | Commenc. Date |  |  | : | 2020-12-01 |  |  | Revised Value |  |  |  |  | : | 25000000 |  |  | DHs |  | Actual Paid | : | 5114186 |  |  | Dhs
Completion Date | : | 2021-12-04 |  |  | Revised Value | : | 22011000 |  | DHs |  | Completion Date |  |  | : | 2021-12-04 |  |  | Potential Changes |  |  |  |  | : | 4000000 |  |  | DHs | 4000000
Approved EOT | : | 150 | Days |  | Potential Changes | : | -5000 |  | DHs | -5000 | Approved EOT |  |  | : | 0 | Days |  | Recap Value |  |  |  |  | : | 1750000 |  |  | DHs |  | Planned Value | : | 41705000 |  |  | Dhs |  | EVI
Revised Date | : | 2022-05-03 |  |  | EAC | : | 22006000 |  | DHs |  | Revised Date |  |  | : | 2021-12-04 |  |  | EAC |  |  |  |  | : | 8750000 |  |  | DHs |  | Earned Value | : | 39375000 |  |  | Dhs
Contract Duration | : | 763 | Days |  | Cumulative Certified | : | 5114190 |  | DHs |  | Contract Duration |  |  | : | 369 | Days |  | Cumulative Certified |  |  |  |  | : | 5114190 |  |  | DHs | [8 empty] | 0.94413
Remain Duration | : | 129 | Days |  | Cumulative Paid | : | 2557093 |  | DHs |  | Remain Duration |  |  | : | -21 | Days |  | Cumulative Paid |  |  |  |  | : | 2557093 |  |  | DHs
Elapsed Duration | : | 634 | Days |  | % Value Paid | : | 11.62% |  |  |  | Elapsed Duration |  |  | : | 390 | Days |  | % Value Paid |  |  |  |  | : | 11.62%
Elapsed Duration |  | 83.09% |  |  | Allocated 2021 | : | By ADM |  | DHs |  | Elapsed Duration |  |  |  | 105.7% |  |  | Allocated 2021 |  |  |  |  | : | By ADM |  |  | DHs | [6 empty] | Description Here
Forecast Date | : | 2022-12-01 |  |  | Certified This Year | : | 5114190 |  | DHs |  | Forecast Date |  |  | : | 2022-12-01 |  |  | Certified This Year |  |  |  |  | : | 5114190 |  |  | DHs
Days of Delay | : | 212 | Days | 212 | Paid this Year | : | 2557093 |  | DHs |  | Days of Delay |  |  | : | 362 | Days | 362 | Paid this Year |  |  |  |  | : | 2557093 |  |  | DHs
Planned Schedual | : | 100% | Percent |  | Planned To Date | : | 0 |  | DHs |  | Planned Schedual |  |  | : | 100% | Percent |  | Planned To Date |  |  |  |  | : | 0 |  |  | DHs
Actual Schedual | : | 50% | Percent |  | Remaining Budget | : | By ADM |  | DHs |  | Actual Schedual |  |  | : | 70% | Percent |  | Remaining Budget |  |  |  |  | : | By ADM |  |  | DHs
SPI | : | 0.5 |  |  | Buget Paid | : | By ADM |  |  |  | SPI |  |  | : | 0.7 |  |  | Buget Paid |  |  |  |  | : | By ADM
Schedule Performance
[29 empty] | Planned | : | 100% |  |  |  |  | SPI
Overall Status of project / Achievements within the month | [18 empty] | Claims and Variations | [9 empty] | Actual | : | 70%
Text Here | [18 empty] | Total Claims |  |  |  |  | : | 3 | [10 empty] | 0.7
[20 empty] | Approved |  |  |  | : | 1
[20 empty] | Rejected |  |  |  | : | 0
[20 empty] | Pend. Contractor |  |  |  | : | 0 | [8 empty] | Description Here
[20 empty] | Pend. Consultant |  |  |  | : | 0
Project Challenges / Critical Issues | [7 empty] | Suggested Solutions & Mitigation Actions | [11 empty] | Pend. ADM |  |  |  | : | 1
Text Here | [7 empty] | Text Here | [10 empty] | Veriation Orders |  |  |  |  | : | 4
[20 empty] | Issued |  |  |  | : | 1
[20 empty] | Approved |  |  |  | : | 1
[20 empty] | Pend. Contractor |  |  |  | : | 0 |  |  |  | Quality Performance
[20 empty] | Pend. Consultant |  |  |  | : | 1 | [6 empty] | Planned |  | Actual |  | Compliance%
[20 empty] | Pend. ADM |  |  |  | : | 1 |  |  |  | NOC's |  | : | 20 |  | 11 |  |  | 55%
Major Project Progress During Next Period | [18 empty] | HSE Status | [9 empty] | Material Submittals |  | : | 20 |  | 20 |  |  | 100%
Text Here | [18 empty] | Incidents |  |  | : | 1 |  |  | Incident |  |  | Shop Drowing Sub. |  | : | 18 |  | 18 |  |  | 100%
[19 empty] | LTIFR |  |  | : | 6.9455 | [5 empty] | Laboratory Tests |  | : | 15 |  | 15 |  |  | 100%
[19 empty] | Training |  |  | : | 15 |  |  | Hours |  |  | Calibration |  | : | 18 |  | 14 |  |  | 77.78%
[19 empty] | HSE NCR's |  |  |  | 1 |  |  | Opened |  |  | Suplier Prequalification |  | : | 56 |  | 43 |  |  | 76.79%
[19 empty] | Works Instructions (WI) | [9 empty] | NCR's Completion |  | : | 95%
[19 empty] | Total |  | 20 |  |  | Closed |  | 7 | 35% |  | RFI's Completion |  | : | 100%
𝑚^2
Note on AK14: Excuding VAT
Note on BE21: Cost Expenditure Index
Note on AI22: Excuding VAT
Note on L23: Excuding VAT
Note on AI23: Amount of Approved VO's + Approved Claims
Note on B24: Commencement Date
Note on L24: Amount of Approved VO's + Approved Claims
Note on Y24: Commencement Date
Note on AI24: Amount Of contract value + Approved changes per DHS
Note on B25: Contract Completion Date
Note on L25: Amount Of contract value + Approved Vos per DHS
Note on Y25: Contract Completion Date
Note on AI25: Amount of Potenial VO's + Potential claims Per DHS
Note on B26: Number of Days of Approved EOT
Note on L26: Amount of Potenial VO's + potential claims Per DHS
Note on Y26: Number of Days of Approved EOT
Note on BE26: Earned Value Index
Note on B27: Authorized Revised Date Based on EOT
Note on L27: Estimated at Completion
Note on Y27: Authorized Revised Date Based on EOT
Note on AI27: Estimated at Completion
Note on B28: Number of Days as Per Contract
Note on L28: Total certified payments up to date
Note on Y28: Number of Days as Per Contract
Note on AI28: Total certified payments up to date
Note on B29: Number of Days
Note on L29: Cumulative Paid to Date without advance Payment
Note on Y29: Number of Days
Note on AI29: Cumulative Paid to Date without advance Payment
Note on B30: Number of Days
Note on L30: % Paid of allocated budget this year
Note on Y30: Number of Days
Note on AI30: % Paid of allocated budget this year
Note on L31: Allocated Budget for the year
Note on AI31: Allocated Budget for the year
Note on B32: Forecast Compition Date : Expected Completion Date by contractor Program, Based on Actual Progress
Note on Y32: Forecast Compition Date : Expected Completion Date by contractor Program, Based on Actual Progress
Note on B33: Number of Days
Note on L34: Cumulative Paid to Date without advance Payment
Note on AI34: Cumulative Paid to Date without advance Payment
Note on L35: Cumulative Paid to Date without advance Payment
Note on AI35: Cumulative Paid to Date without advance Payment
Note on L36: % Paid of allocated budget this year
Note on AI36: % Paid of allocated budget this year
Note on AJ54: Lost Time Injury Frequency Rate

## Acheivements
Project Name : Project X
xxx - xxxxxxx- xx
Acheivement Summary Report
# | Major Project Progress Tasks & Construction Performance During This Period | Month/Year
1 | text 1 | 2021-01-01
2 | text 2 | 2021-02-01
3
4
5
6
7
8
9
10
11
12
13
14
15
# | Major Project Progress Tasks & Construction Performance During Next Period | Month/Year
1 | text 1 | 2021-01-01
2 | text 2 | 2021-02-01
3
4
5
6
7
8
9
10
11
12
13
14
15
# | Cumulative Major Project Progress Tasks & Construction Performance | Month/Year
1 | text 1 | 2021-01-01
2 | text 2 | 2021-02-01
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Schedule
Project Name : Project X
xxx - xxxxxxx- xx
Project Schedule Report
Show the status of the project major activities against schedule by completing the following table.
# | Major Activities ( To be agreed with ADM Team at the time of approval baseline ) | Completion Date |  |  | Completion Percentage |  |  |  | Status | Remarks / Brief Reasons for Status
|  | Planned | Actual | Forecast | % Planed | % Completion as per last Report | Actual% to date
1 | Activity 1 | 2021-03-10 | 2021-03-11 |  | 50% | 15% | 10% | 10% | Delayed
2 | Activity 2 | 2021-03-10 | 2021-03-11 |  | 40% | 35% | 40% | 40% | As Plan
3 | Activity 3 | 2021-03-10 | 2021-03-11 |  | 80% | 77% | 82% | 82% | Exceed Plan
Note on B8: Major Project Progress Tasks & Construction Performance During This Period
Note on C9: Planned Completion Date (the date by which related Activity was Planned for Completion). As per the approved programme.
Note on D9: Actual Completion Date (the actual date when related activity was completed).
Note on E9: Forecast Completion Date (the New date which the related activity is forecasted to be completed).

## Commercial Status C
Project Name : Project X
xxx - xxxxxxx- xx
Project Commercial Status Report - Contrctor
Show the status of the project from Actual Expenditure point of view for contractor by completing the following tables:
Contract Information
| Contractor Name | Text Here
| Contract Number | abc-3512-4521
| Time |  |  |  | Total Contract Budget (DHs) |  |  |  |  | Budget This Year (DHs)
| Award Date | 2020-04-02 |  |  | Contract Value |  | 22000000 | Dhs |  | Budget This Year |  | By ADM | Dhs
| Commencement Date | 2020-12-01 |  |  | Approved VO's |  | 2000000 | Dhs |  | Total Certified This Year |  | 5114190 | Dhs
| Completion Date | 2021-12-04 |  |  | Approved Claims |  | 1000000 | Dhs |  | Total Paid This Year |  | 2557093 | Dhs
| Approved EOT | 0 | Days |  | Revised Value |  | 25000000 | Dhs |  | Report Period | From | 2021-01-01
| Revised Date | 2021-12-04 |  |  | Potent. VO's ¦ Save |  | 3000000 | Dhs |  |  | To | 2021-12-31
| Contract Duration | 369 | Days |  | Recap Value |  | 1750000 | Dhs |  | Planned To Date |  | 0 | Dhs
| Elapsed Duration | 389 | Days |  | Potential Claims |  | 1000000 | Dhs |  | Compliance to Budget % |  | By ADM
| 105.4% |  |  |  | Estimated at Competion (EAT) |  | 8750000 | Dhs |  | Remaining Budget |  | By ADM | Dhs
[5 empty] | Cumulative Certified |  | 5114190 | Dhs |  | Budget Paid |  | By ADM
[5 empty] | Cumulative Paid |  | 2557093 | Dhs |  | CPI |  | By ADM
[5 empty] | Remaining Value |  | 19442907 | Dhs
11.62%
Planned Cash Flow for This Year (DHs)
| Month | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
| Planned By ADM (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Planned ADM (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Planned (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bank Guarantees
# | Guarantee No | 2021-01-01: Guarantee Type; 2021-03-01: Guarantee Amount (AED); 2021-05-01: Valid Till
1
2
3
Advance Payments Status |  | 2021-06-01: Retention Money Status
Advance Payment (AED) |  | 2021-01-01: Recovered Amount (AED); 2021-03-01: Balance Advance Payment (AED); 2021-06-01: Retention Money withheld to Date; 2021-09-01: Retention Money released to Date; 2021-11-01: Balance Retention Mony (AED)
1278546 |  | 2021-01-01: 1278546; 2021-03-01: 0; 2021-06-01: 1278546; 2021-09-01: 1278546; 2021-11-01: 0
Comments |  | 2021-06-01: Comments
Progress Payments
# | Invoice Number | 2021-01-01: Invoice Date (Cut-off Date); 2021-03-01: Payment Value DHS; 2021-05-01: Submission Date; 2021-07-01: Approval Date; 2021-09-01: Status; 2021-10-01: Clearance Date; 2021-11-01: Comments
[8 empty] | Engineer | ADM
1 | B524685 | 2021-01-01: 2021-04-04; 2021-03-01: 1278546; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-04; 2021-08-01: 2021-04-04; 2021-09-01: Paid; 2021-10-01: 2021-04-04
2 | B524686 | 2021-01-01: 2021-04-05; 2021-03-01: 1278547; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-04; 2021-08-01: 2021-04-04; 2021-09-01: Paid; 2021-10-01: 2021-04-05
3 | B524687 | 2021-01-01: 2021-04-06; 2021-03-01: 1278548; 2021-05-01: 2021-03-04; 2021-07-01: 2021-04-04; 2021-08-01: 2021-04-04; 2021-09-01: Not Yet
4 | B524688 | 2021-01-01: 2021-04-07; 2021-03-01: 1278549; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-04; 2021-08-01: 2021-04-04; 2021-09-01: Not Yet
Note on L12: To be filled by ADM Teams
Note on B15: Total Approved EOT by Number of Days calculated from claims + VO's
Note on B16: Revised Complition Date based on the approved EOT
Note on B17: Per Days
Note on B18: Per Days
Note on B26: For ADM Team Use
Note on B28: For ADM Team Use

## Commercial Status E
Project Name : Project X
xxx - xxxxxxx- xx
Project Commercial Status Report - Consultant
Show the status of the project from Actual Expenditure point of view for consultant by completing the following tables:
Contract Information
| Consultant Name | Text Here
| Contract Number | abc-3512-4521
| Time |  |  |  | Total Contract Budget (DHs) |  |  |  |  | Budget This Year (DHs)
| Award Date | 2020-04-02 |  |  | Contract Value |  | 22000000 | Dhs |  | Budget This Year |  | By ADM | Dhs
| Commencement Date | 2020-04-01 |  |  | Approved.Vos / EOT (Dhs) |  | 11000 | Dhs |  | Total Certified This Year |  | 5114190 | Dhs
| Completion Date | 2021-12-04 |  |  | Revised Value |  | 22011000 | Dhs |  | Total Paid This Year |  | 2557093 | Dhs
| Approved EOT | 150 | Days |  | Potent.Vos / EOT / Save (Dhs) |  | -5000 | Dhs |  | Report Period | From | 2021-01-01
| Revised Date | 2022-05-03 |  |  | Estimated at Competion (EAT) |  | 22006000 | Dhs |  |  | To | 2021-12-31
| Contract Duration | 763 | Days |  | Cumulative Certified |  | 5114190 | Dhs |  | Planned To Date |  | 0 | Dhs
| Elapsed Duration | 633 | Days |  | Cumulative Paid |  | 2557093 | Dhs |  | Compliance to Budget % |  | By ADM
| 82.96% |  |  |  | Remaining Value |  | 19442907 | Dhs |  | Remaining Budget |  | By ADM | Dhs
[5 empty] | 11.62% |  |  |  |  | Budget Paid |  | By ADM
[10 empty] | CPI |  | By ADM
Planned Cash Flow for this Year (DHs)
| Month | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
| Planned By ADM (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Planned ADM (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Planned (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumulative Planned (DHs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Progress Payments
# | Invoice Number | 2021-01-01: Invoice Date (Cut-off Date); 2021-03-01: Payment Value (Excuding VAT) DHS; 2021-05-01: Submission Date; 2021-07-01: ADM Approval Date; 2021-09-01: Status; 2021-10-01: Clearance Date; 2021-11-01: Comments
1 | B524685 | 2021-01-01: 2021-04-04; 2021-03-01: 1278546; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-04; 2021-09-01: Paid; 2021-10-01: 2021-04-04
2 | B524686 | 2021-01-01: 2021-04-05; 2021-03-01: 1278547; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-05; 2021-09-01: Paid; 2021-10-01: 2021-04-05
3 | B524687 | 2021-01-01: 2021-04-06; 2021-03-01: 1278548; 2021-05-01: 2021-03-04; 2021-07-01: 2021-04-06; 2021-09-01: Not Yet
4 | B524688 | 2021-01-01: 2021-04-07; 2021-03-01: 1278549; 2021-05-01: 2021-04-04; 2021-07-01: 2021-04-07; 2021-09-01: Not Yet | Type | Advance
Note on L12: For ADM Team Use
Note on B15: Total Approved EOT by Number of Days
Note on B16: Revised Complition Date based on the approved EOT
Note on B17: Per Days
Note on G17: Comulative Certified To date (DHs)
Note on B18: Per Days
Note on G18: Comulative Paid To date (DHs)
Note on B24: For ADM Team Use
Note on B26: For ADM Team Use

## Quality Status
Project Name : Project X
xxx - xxxxxxx- xx
Project Quality Status Report
# | Quality Item | Cumulative to Date | [6 empty] | This Month |  |  |  | Pending Last Month | Brief Summary for Status during this Month
|  | Total | Planned | Actual | Completion % | Status |  |  | Planned | Actual | Completion % | Pending for >14 Days
[6 empty] | Approved | Rejected | Pending / Open
1 | NOC's * | 20 | 20 | 11 | 55% | 0 | 0 | 0 | 2 | 2 | 100% | 0 | 0
2 | Method of Statements | 30 | 30 | 28 | 93.33% | 0 | 0 | 0 | 2 | 1 | 50% | 0 | 0
3 | Laboratory Tests * | 15 | 15 | 15 | 100% | 0 | 0 | 0 | 2 | 2 | 100% | 0 | 0
4 | Maintinance & Calibration Reports * | 18 | 18 | 14 | 77.78% | 0 | 0 | 0 | 2 | 1 | 50% | 0 | 0
5 | Third Parties Reports * | 22 | 22 | 11 | 50% | 0 | 0 | 0 | 2 | 2 | 100% | 0 | 0
6 | Sub-Contractors Prequalification | 40 | 40 | 38 | 95% | 0 | 0 | 0 | 2 | 1 | 50% | 0 | 0
7 | Suplier Prequalification | 16 | 16 | 5 | 31.25% | 0 | 0 | 0 | 2 | 2 | 100% | 0 | 0
8 | Material Submittal * | 20 | 20 | 20 | 100% | 0 | 0 | 0 | 2 | 1 | 50% | 0 | 0
9 | Shop Drowings Submittal * | 18 | 18 | 18 | 100% | 0 | 0 | 0 | 2 | 2 | 100% | 0 | 0
10 | Daily Report * | 50 | 50 | 49 | 98% | 0 | 0 | 0 | 2 | 1 | 50% | 0 | 0
* Copy of documents for this month only to be attached as a appendex
# | Quality Item | Cumulative to Date |  |  |  | This Month |  |  |  | Pending Last Month | Brief Summary for Status during this Month
|  | Total | Closed | Pending / Open | Complition % | Total | Closed | Pending / Open | Completion %
1 | Non-Conformity Reports (NCR's) * | 20 | 19 | 1 | 95% | 3 | 1 | 2 | 33.33% | 0
2 | Site Instructions (SI) * | 30 | 23 | 7 | 76.67% | 5 | 4 | 1 | 80% | 0
3 | Visit Observation * | 50 | 44 | 6 | 88% | 4 | 4 | 0 | 100% | 0
4 | Request for Informations (RFI's) * | 40 | 40 | 0 | 100% | 3 | 3 | 0 | 100% | 0
* Copy of documents for this month only to be attached as a appendex
# | Quality Item | Cumulative to Date |  |  |  |  | This Month |  |  |  |  | Brief Summary for Status during this Month
|  | Total | Approved | Rejected | Pending / Open | Complition % | Total | Rejected | Approved | Pending / Open | Completion %
1 | Work Instruction Request (WIR) * | 20 | 2 | 5 | 13 | 35% | 5 | 2 | 2 | 1 | 80%
* Copy of documents for this month only to be attached as a appendex
Note on C8: Total Submittals for Project
Note on D8: Comulative Planned Submittals till report date
Note on E8: Comulative Actual submittals till report date
Note on J8: Planned Submittals this month
Note on K8: Actual Submittals this month
Note on G9: Approved & Approved as noted
Note on B23: Major Project Progress Tasks & Construction Performance During This Period
Note on C24: Total Submittals for Project
Note on D24: Comulative Actual submittals till report date
Note on E24: Comulative Actual submittals till report date
Note on G24: Total Submittals for Project
Note on H24: Comulative Actual submittals till report date
Note on I24: Comulative Actual submittals till report date
Note on B26: Planned : NCR's with Planned Corrective Actions Up to Date
Note on B27: Planned : Instructions with Planned Corrective Actions Up to Date
Note on B28: Planned : Observations with Planned Corrective Actions Up to Date
Note on B33: Major Project Progress Tasks & Construction Performance During This Period
Note on C34: Total Submittals for Project
Note on D34: Comulative Actual submittals till report date
Note on F34: Comulative Actual submittals till report date
Note on H34: Total submittals this month
Note on I34: Total Submittals for Project
Note on J34: Comulative Actual submittals till report date
Note on K34: Comulative Actual submittals till report date

## Project Issues
Project Name : Project X
xxx - xxxxxxx- xx
Project Issues Report
Describe each high priority issue and impact rate on the project by completing the following table:
# | Issue | Impact |  |  | Mitigation Action | Owner * | Status | Remarks
|  | Category | Rate % | Assessment
1 |  | HSE | 20% | Low |  |  | Resolved
2
3
4
5
6
7
8
9
10
11
12
Note on A7: Issue : The high priority issues raised during the reporting period of pending from the previous reports
Note on B7: Issue : The high priority issues raised during the reporting period of pending from the previous reports
Note on C7: The impact rating of each identified issue
Note on F7: A desctiption of the action required
Note on G7: i.e. ADM, Consultant, Contractor, Others

## Critical Submitals
Project Name : Project X
xxx - xxxxxxx- xx
Major / Critical Submittals Log
Critical submittals which might have impact to the schedule
# | Type of Submittal | Major Submittals that might affect the project Target Completion Date (Brief Description) | Status | Planned Submission Date | Actual Submission Date | Planned Approval Date | Actual Approval Date | Impact to the Schedule | Remarks
1 | Method Statement |  | Not Submitted |  |  |  |  | Moderate ( Between 5% - 10%)
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on B7: Issue : The high priority issues raised during the reporting period of pending from the previous reports
Note on C7: Brief Description : For the Critical submittals which might have impact to the schedule
Note on D7: Pending = submitted and not responded yet

## Risk Register
Project Name : Project X
xxx - xxxxxxx- xx
Project Risk Register
Show the risk register associated with the project activities by completing the following table:
| # | DATE | الخطر HAZARD/ RISKS INVOLVED | وصف الخطر RISK DESCRIPTION | جهة الخطر Risk Owner | تقييم الخطر الأولي INITIAL RISK ASSESSMENT |  |  | إجراءات السيطرة والتحكم RISK CONTROL MEASURE | تقييم الخطر المتبقي RESIDUAL RISK ASSESSMENT |  |  | خطة خفض الخطر MITIGATION PLAN | الجهة المسؤولة عن التنفيذ RESPONSIBLE | تاريخ الاستحقاق DUE DATE | الحالة STATUS | ملاحظات COMMENTS
[6 empty] | الاحتمالية PROBABILITY | التأثير IMPACT | التقييم RISK SCORE |  | الاحتمالية PROBABILITY | التأثير IMPACT | التقييم RISK SCORE
QUALITY
| 1 | 2018-08-01 | Not commitment to technical specification | Failure of consultants and contractors to comply with approved Infrastructure technical specifications in design and constructions will lead to nonconforming Infrastructure assets | External & Internal | 3 | 4 | 12 | _ Design Approval Process. _ Materials testing and acceptance process. _ Material submittals and samples process. _ Quality control and inspection process. _ Approval of QA/QC project plan. _ Project manager site visits _ QA/QC reporting process. _ Assets Handing Over Process. | 1 | 3 | 3 | No Action Required
| 2 | 2018-08-02 | [5 empty] | 0 |  |  |  | 0
| 3 | 2018-08-03 | [5 empty] | 0 |  |  |  | 0
| 4 | 2018-08-04 | [5 empty] | 0 |  |  |  | 0
| 5 | 2018-08-05 | [5 empty] | 0 |  |  |  | 0
| 6 | 2018-08-06 | [5 empty] | 0 |  |  |  | 0
| 7 | 2018-08-07 | [5 empty] | 0 |  |  |  | 0
| 8 | 2018-08-08 | [5 empty] | 0 |  |  |  | 0
| 9 | 2018-08-09 | [5 empty] | 0 |  |  |  | 0
| 10 | 2018-08-10 | [5 empty] | 0 |  |  |  | 0
SCHEDULE
| 1 | 2019-04-16 | [5 empty] | 0 |  |  |  | 0
| 2 | 2018-09-22 | [5 empty] | 0 |  |  |  | 0
| 3 | 2018-09-26 | [5 empty] | 0 |  |  |  | 0
| 4 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 5 | 2018-12-29 | [5 empty] | 0 |  |  |  | 0
| 6 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 7 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 8 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 9 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
| 10 | 2018-08-02 | [5 empty] | 0 |  |  |  | 0
FINANCIAL
| 1 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
| 2 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
| 3 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
| 4 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
HSE
| 1 | 2018-09-25 | [5 empty] | 0 |  |  |  | 0
| 2 | 2020-03-20 | [5 empty] | 0 |  |  |  | 0
| 3 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 4 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 5 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 6 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 7 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 8 | [6 empty] | 0 |  |  |  | 0
LEGAL - CONTRACTUAL
| 1 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
| 2 | 2020-03-15 | [5 empty] | 0 |  |  |  | 0
| 3 | 2019-02-02 | [5 empty] | 0 |  |  |  | 0
| 4 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 5 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 6 | 2018-09-28 | [5 empty] | 0 |  |  |  | 0
| 7 | 2018-08-01 | [5 empty] | 0 |  |  |  | 0
Other
| 1 | [6 empty] | 0 |  |  |  | 0
| 2 | [6 empty] | 0 |  |  |  | 0
| 3 | [6 empty] | 0 |  |  |  | 0
| 4 | [6 empty] | 0 |  |  |  | 0
| 5 | [6 empty] | 0 |  |  |  | 0
| 6 | [6 empty] | 0 |  |  |  | 0
| 7 | [6 empty] | 0 |  |  |  | 0
| 8 | [6 empty] | 0 |  |  |  | 0
| 9 | [6 empty] | 0 |  |  |  | 0
| 10 | [6 empty] | 0 |  |  |  | 0
| 11 | [6 empty] | 0 |  |  |  | 0
Note on B6: For Risk Management Methodology, Please refer to Sheet (DC)
Note on F7: Internal : Project Owner and Teams including (ADM - Consultant - Contractor) External : Other Entities

## Earned Value & Progress
Project Name : Project X
xxx - xxxxxxx- xx
Project Earned Value and Project Progress - Cost VS Time
CashFlow Against time (Planned Vs Actual)
Contract Value |  | 25000000
Earned Value |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned Monthly Value |  | 2000 | 3000 | 20000 | 100000 | 1004000 | 1908000 | 2812000 | 3716000 | 4620000 | 5524000 | 6428000 | 7332000 | 8236000 | 9140000 | 10044000 | 10948000 | 11852000 | 3322000 | 323000 | 3200030 | 100000 | 1004000 | 1908000 | 2812000
Monthly (Planned) % | % Monthly (Planned) | 0.008% | 0.012% | 0.08% | 0.4% | 4.016% | 7.632% | 11.25% | 14.86% | 18.48% | 22.1% | 25.71% | 29.33% | 32.94% | 36.56% | 40.18% | 43.79% | 47.41% | 13.29% | 1.292% | 12.8% | 0.4% | 4.016% | 7.632% | 11.25%
Actual Monthly Value | Actual Monthly Value | 3000 | 4000 | 20000 | 100000 | 1004000 | 1908000 | 2812000 | 3716000 | 4620000 | 5524000 | 6428000 | 5000000 | 8236000 | 9140000 | 10044000 | 10948000 | 11852000 | 3322000 | 323000 | 3200030 | 5000 | 500000 | 500000 | 1000000
Monthly (Actual) % | % Monthly (Actual) | 0.012% | 0.016% | 0.08% | 0.4% | 4.016% | 7.632% | 11.25% | 14.86% | 18.48% | 22.1% | 25.71% | 20% | 32.94% | 36.56% | 40.18% | 43.79% | 47.41% | 13.29% | 1.292% | 12.8% | 0.02% | 2% | 2% | 4%
Planned Cumulative Value | Planned Comulative Value | 2000 | 5000 | 25000 | 125000 | 1129000 | 3037000 | 5849000 | 9565000 | 14185000 | 19709000 | 26137000 | 33469000 | 41705000 | 50845000 | 60889000 | 71837000 | 83689000 | 87011000 | 87334000 | 90534030 | 90634030 | 91638030 | 93546030 | 96358030
Cumulative (Planned) % | %commulative (Planned) | 0.008% | 0.02% | 0.1% | 0.5% | 4.516% | 12.15% | 23.4% | 38.26% | 56.74% | 78.84% | 104.5% | 133.9% | 166.8% | 203.4% | 243.6% | 287.3% | 334.8% | 348% | 349.3% | 362.1% | 362.5% | 366.6% | 374.2% | 385.4%
Actual Comulative Value | Actual Comulative Value | 3000 | 7000 | 27000 | 127000 | 1131000 | 3039000 | 5851000 | 9567000 | 14187000 | 19711000 | 26139000 | 31139000 | 39375000 | 48515000 | 58559000 | 69507000 | 81359000 | 84681000 | 85004000 | 88204030 | 88209030 | 88709030 | 89209030 | 90209030
Cumulative (Actual) % | %commulative (Actual) | 0.012% | 0.028% | 0.108% | 0.508% | 4.524% | 12.16% | 23.4% | 38.27% | 56.75% | 78.84% | 104.6% | 124.6% | 157.5% | 194.1% | 234.2% | 278% | 325.4% | 338.7% | 340% | 352.8% | 352.8% | 354.8% | 356.8% | 360.8%
Physical Progress |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 2% | 5% | 8% | 11% | 14% | 17% | 20% | 23% | 26% | 29% | 32% | 35% | 38% | 41% | 44% | 47% | 50% | 53% | 56% | 59% | 62% | 65% | 68% | 71%
Cumulative Planned | Cumm. Plan | 2% | 7% | 15% | 26% | 40% | 57% | 77% | 100% | 126% | 155% | 187% | 222% | 260% | 301% | 345% | 392% | 442% | 495% | 551% | 610% | 672% | 737% | 805% | 876%
Actual | Actual | 2% | 6% | 10% | 14% | 18% | 22% | 26% | 30% | 34% | 38% | 42% | 46% | 50% | 54% | 58% | 62% | 66% | 70% | 74% | 78% | 82% | 86% | 90% | 94%
Cumulative Actual | Cumm. Actual | 2% | 8% | 10% | 24% | 42% | 64% | 90% | 120% | 154% | 192% | 234% | 280% | 330% | 384% | 442% | 504% | 570% | 640% | 714% | 792% | 874% | 960% | 1050% | 1144%

## Resources
Project Name : Project X
xxx - xxxxxxx- xx
Resources Histogram Report
Labor Resources & Equipment Resources Against time (Planned Vs Actual)
ManPowers |  |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Average Monthly Planned |  |  | 22 | 132 | 22 | 21 | 22 | 22 | 12 | 22 | 242 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 132 | 22 | 22
Average Monthly Actual |  |  | 22 | 143 | 21 | 9 | 22 | 22 | 11 | 21 | 264 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 22 | 22
Cumulative Planned |  |  | 572 | 4004 | 4576 | 5122 | 5694 | 6266 | 6578 | 7150 | 13442 | 16874 | 20306 | 23738 | 27170 | 30602 | 34034 | 37466 | 40898 | 44330 | 47762 | 51194 | 54626 | 58058 | 58630 | 59202
Cumulative Actual |  |  | 572 | 4290 | 4836 | 5070 | 5642 | 6214 | 6500 | 7046 | 13910 | 17628 | 21346 | 25064 | 28782 | 32500 | 36218 | 39936 | 43654 | 47372 | 51090 | 54808 | 58526 | 62244 | 62816 | 63388
Actually Provided on site (As per Baseline) | Labor | Planned | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2
| Mason | Planned | 2 | 4 | 2 | 2 | 2 | 2 | 1 | 2 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2
|  | Actual | 2 | 5 | 2 | 1 | 2 | 2 | 1 | 2 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2
| Electrician | Planned | 2 | 6 | 2 | 2 | 2 | 2 | 1 | 2 | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2
|  | Actual | 2 | 7 | 2 | 1 | 2 | 2 | 1 | 2 | 12 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 2 | 2
| Operator | Planned | 2 | 8 | 2 | 2 | 2 | 2 | 1 | 2 | 14 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2
|  | Actual | 2 | 9 | 2 | 1 | 2 | 2 | 1 | 2 | 16 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 2 | 2
| Tiler | Planned | 2 | 10 | 2 | 2 | 2 | 2 | 1 | 2 | 18 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 2
|  | Actual | 2 | 11 | 2 | 0 | 2 | 2 | 1 | 2 | 20 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 2 | 2
| Plumber/Pipe Fitter | Planned | 2 | 12 | 2 | 2 | 2 | 2 | 1 | 2 | 22 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 2 | 2
|  | Actual | 2 | 13 | 2 | 0 | 2 | 2 | 1 | 2 | 24 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 2 | 2
| Gardener | Planned | 2 | 14 | 2 | 2 | 2 | 2 | 1 | 2 | 26 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 2 | 2
|  | Actual | 2 | 15 | 2 | 0 | 2 | 2 | 1 | 2 | 28 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 2 | 2
| Carpenter | Planned | 2 | 16 | 2 | 2 | 2 | 2 | 1 | 2 | 30 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 2 | 2
|  | Actual | 2 | 17 | 2 | 1 | 2 | 2 | 1 | 2 | 32 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 2 | 2
| Painter | Planned | 2 | 18 | 2 | 2 | 2 | 2 | 1 | 2 | 34 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 2 | 2
|  | Actual | 2 | 19 | 2 | 1 | 2 | 2 | 1 | 2 | 36 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 2 | 2
| Irrigation Technician | Planned | 2 | 20 | 2 | 2 | 2 | 2 | 1 | 2 | 38 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 2 | 2
|  | Actual | 2 | 21 | 2 | 1 | 2 | 2 | 1 | 2 | 40 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 2 | 2
| Steel Fixer | Planned | 2 | 22 | 2 | 1 | 2 | 2 | 1 | 2 | 42 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 2 | 2
|  | Actual | 2 | 23 | 2 | 2 | 2 | 2 | 1 | 2 | 44 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 2 | 2
| Other | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EQUIPMENT |  |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Average Monthly Planned |  |  | 16 | 23 | 16 | 23 | 16 | 9 | 9 | 16 | 16 | 23 | 23 | 16 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 16 | 16 | 16 | 16 | 16
Average Monthly Actual |  |  | 16 | 24 | 16 | 24 | 16 | 8 | 8 | 8 | 16 | 24 | 24 | 16 | 16 | 24 | 24 | 8 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16
Cumulative Planned |  |  | 416 | 1014 | 1430 | 2028 | 2444 | 2678 | 2912 | 3328 | 3744 | 4342 | 4940 | 5356 | 5954 | 6552 | 7150 | 7748 | 8346 | 8944 | 9542 | 9958 | 10374 | 10790 | 11206 | 11622
Cumulative Actual |  |  | 416 | 1040 | 1456 | 2080 | 2496 | 2704 | 2912 | 3120 | 3536 | 4160 | 4784 | 5200 | 5616 | 6240 | 6864 | 7072 | 7696 | 8320 | 8944 | 9360 | 9776 | 10192 | 10608 | 11024
Actually Provided on site | JCB | Planned | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Tipper truck | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Excavator | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Mobile Cranes | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Generators | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Plate Compactor | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Buses | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
| Other | Planned | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Actual | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
|  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## KPIs
Project Name : Project X
xxx - xxxxxxx- xx
Project KPI's Report as Approved Baseline
KPI - 01 |  | KPI-1 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 02 |  | 2020-12-31: KPI-2 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 03 |  | 2020-12-31: KPI-3 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 04 |  | 2020-12-31: KPI-4 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 05 |  | 2020-12-31: KPI-5 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 06 |  | 2020-12-31: KPI-6 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 07 |  | 2020-12-31: KPI-7 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44
KPI - 08 |  | 2020-12-31: KPI-8 Description ( Including units)
Month |  | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30
Planned | Plan | 0.02 | 0.05 | 0.08 | 0.11 | 0.14 | 0.17 | 0.2 | 0.23 | 0.26 | 0.29 | 0.32 | 0.35 | 0.38 | 0.41 | 0.44 | 0.47 | 0.5 | 0.53 | 0.56 | 0.59 | 0.62 | 0.65 | 0.68 | 0.71
Cumulative Planned | Cumm. Plan | 0.02 | 0.07 | 0.15 | 0.26 | 0.4 | 0.57 | 0.77 | 1 | 1.26 | 1.55 | 1.87 | 2.22 | 2.6 | 3.01 | 3.45 | 3.92 | 4.42 | 4.95 | 5.51 | 6.1 | 6.72 | 7.37 | 8.05 | 8.76
Actual | Actual | 0.02 | 0.06 | 0.1 | 0.14 | 0.18 | 0.22 | 0.26 | 0.3 | 0.34 | 0.38 | 0.42 | 0.46 | 0.5 | 0.54 | 0.58 | 0.62 | 0.66 | 0.7 | 0.74 | 0.78 | 0.82 | 0.86 | 0.9 | 0.94
Cumulative Actual | Cumm. Actual | 0.02 | 0.08 | 0.1 | 0.24 | 0.42 | 0.64 | 0.9 | 1.2 | 1.54 | 1.92 | 2.34 | 2.8 | 3.3 | 3.84 | 4.42 | 5.04 | 5.7 | 6.4 | 7.14 | 7.92 | 8.74 | 9.6 | 10.5 | 11.44

## Progress Photos
Project Name : Project X
Contract Number : abc-3512-4521
Progress Photos
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description
Photo Here | Photo Here
Photo Description | Photo Description

## Claims Status
Project Name : Project X
Contract Number : abc-3512-4521
Project Claims Status Log
Show the status of the project Claims by completing the following table:
# | Contractor Claim | [5 empty] | Engineer Response | [5 empty] | ADM |  |  |  |  | Final Status | Remarks
| Description | Events References | EOT (Days) | Cost (DHs) | Submission Date | Doc Refrence | Engineer Recommendation | Recommended EOT (Days) | Recommended Cost (DHs) | Response Date | Doc Reference | Response | ADM Reply | Approved EOT (Days) | Approved Cost (DHs) | Reply Date | Doc Reference
1 | Claim | aaa, bbb | 20 | 1000000 | 2021-01-12 | xxx-xxxx-xxxxxx | Text Here | 20 | 1000000 | 2021-01-12 | xxx-xxxx-xxxxxx | Recommended | Text Here | 20 | 1000000 | 2021-01-12 | xxx-xxxx-xxxxxx | Pending ADM
2 | Claim |  | 20 | 1000000 | 2021-01-13 | xxx-xxxx-xxxxxx | Text Here | 20 | 1000000 | 2021-01-13 | xxx-xxxx-xxxxxx | Not recommended | Text Here | 20 | 1000000 | 2021-01-13 | xxx-xxxx-xxxxxx | Approved
3 | Claim |  | 20 | 1000000 | 2021-01-14 | xxx-xxxx-xxxxxx | Text Here | 20 | 1000000 | 2021-01-14 | xxx-xxxx-xxxxxx | Partially recommended | Text Here | 20 | 1000000 | 2021-01-14 | xxx-xxxx-xxxxxx | Pending
4
5
6
7
8
9
10
Note on S7: Approved : Variation has been completed and addendum has been issued to contract Rejected : Variation has been rejected from ADM Pending Contractor : Awaiting contractor action Pending Engineer : Awaiting consultant action Pending ADM : Awaiting employer action

## Claims Details
Project Name : Project X
xxx - xxxxxxx- xx
Detailed Claims Trends Register
Shows detailed information about events of claimes
# | CONTRACTOR'S LETTER REFERENCE | TITLE | Event Reference | EVENT DATE | NOTICE DUE DATE (28 Days) | ACTUAL SUBMISSION | CLAIM DUE DATE | ACTUAL SUBMISSION | Interim Claim Reference | INTERIM CLAIM SUBMISSION | FINAL CLAIM SUBMISSION | ENGINEER'S RESPONSE | ACTUAL SUBMISSION | MERIT | PRINCIPLE | IMPACT ON PROGRAMME | IMPACT ON TIME FOR COMPLETION | IMPACT ON CONTRACT PRICE | RELATED CORRESPONDENCE | FURTHER ACTION BY | DESCRIPTION OF FURTHER ACTION
1 | XXX-XXXX-XXXXXXXXX | Notice of Claim for xxxxxxxx | aaa | 2018-05-05 | 2018-06-02 | 2018-05-28 |  | 2018-06-15 | 1 | YES | NO | 2018-07-27 |  | TBA | YES | TBA | TBA | TBA | XXX-XXXX-XXXXXXXXX |  | CLAIM TO BE REJECTED IN PRINCIPLE
2 | XXX-XXXX-XXXXXXXXX | Notice of Claim for xxxxxxxx | bbbb | 2018-05-06 | 2018-06-03 | 2018-05-29 |  | 2018-06-16 | 1 | YES | NO | 2018-07-28 |  | TBA | YES | TBA | TBA | TBA | XXX-XXXX-XXXXXXXXX |  | ASSESS CLAIM
Formulas:
NOTICE DUE DATE (28 Days) = IF([EVENT DATE]="","",[EVENT DATE]+28)
ENGINEER'S RESPONSE = IF([ACTUAL SUBMISSION]="","",[ACTUAL SUBMISSION]+42)

## Employer's Claims
Project Name : Project X
xxx - xxxxxxx- xx
Employer's Claim Trends Register
Shows detailed information about events of claimes
# | Description | Notification Ref | Date | Amount (AED) | Status | Remarks
1 | Notice of Claim for xxxxxxxx | XXX-XXXX-XXXXXXXXX | 2018-05-05 | 1000000 | Deducted from Contractor's Payment
2 | Notice of Claim for xxxxxxxx | XXX-XXXX-XXXXXXXXX | 2018-05-06 | 200000 | Notified to Contractor

## VOs Status
Project Name : Project X
xxx - xxxxxxx- xx
Project Variation Detailes
| Potential Variation | 1000000 | Dhs
| Instructed Variation | 1000000 | Dhs
| Approved Variation | 3000000 | Dhs
# | Variation Type | Description of the Variation | Employer's Instruction |  | Engineer's Instruction |  |  | Contractor's proposal |  |  |  |  | Engineer's response |  |  |  |  | Engineer's recommendation |  |  |  | VO Type | Measurement Type | Employer's Variation Order |  |  |  | Signature by the Parties (Date) | Current Status | Comments | Action by Date
|  |  | Correspondence |  | Correspondence |  |  | Correspondence |  |  | Amount (AED) | Time Impact if any (days) | Correspondence |  |  | Evaluated Amount (AED) | Remarks | Correspondence |  |  | Amount (AED) |  |  | Ref. No. | Date | Amount (AED) | Time Impact if any (days)
|  |  | Ref. No. | Date | Ref. No. | Date | Type | Ref. No. | Date | Type |  |  | Ref. No. | Date | Type |  |  | Ref. No. | Date | Type
1 | Approved Variation | aaa | xxx - xxx - xxxxxx | 2021-01-01 | xxx - xxx - xxxxxx | 2021-01-01 | Eng. Request for proposal | xxx - xxx - xxxxxx | 2021-01-01 | Response | 1000000 | 20 | xxx - xxx - xxxxxx | 2021-01-01 | Not recommended | 1000000 | Text Here | xxx - xxx - xxxxxx | 2021-01-01 | Approval with comments | 1000000 | BOQ Rate & New Rates | Measurable | xxx - xxx - xxxxxx | 2021-01-01 | 2000000 | 20 | 2021-01-01 | Issued | Text Here | 2021-01-01
2 | Instructed Variation | aaa | xxx - xxx - xxxxxx | 2021-01-02 | xxx - xxx - xxxxxx | 2021-01-02 | Eng. Request for proposal | xxx - xxx - xxxxxx | 2021-01-02 | Contractor's Proposal | 1000000 | 20 | xxx - xxx - xxxxxx | 2021-01-02 | Recommended | 1000001 | Text Here | xxx - xxx - xxxxxx | 2021-01-02 | Approval with comments | 1000001 | New Rate | Lump Sum | xxx - xxx - xxxxxx | 2021-01-02 | 1000000 | 20 | 2021-01-02 | Pending Engineer | Text Here | 2021-01-02
3 | Approved Variation | aaa | xxx - xxx - xxxxxx | 2021-01-03 | xxx - xxx - xxxxxx | 2021-01-03 | Eng. Request for proposal | xxx - xxx - xxxxxx | 2021-01-03 | Contractor's Proposal | 1000000 | 20 | xxx - xxx - xxxxxx | 2021-01-03 | Partially recommended | 1000002 | Text Here | xxx - xxx - xxxxxx | 2021-01-03 | Approval with comments | 1000002 | BOQ Rate | Measurable | xxx - xxx - xxxxxx | 2021-01-03 | 1000000 | 20 | 2021-01-03 | Pending ADM | Text Here | 2021-01-03
4 | Potential Variation | aaa | xxx - xxx - xxxxxx | 2021-01-04 | xxx - xxx - xxxxxx | 2021-01-04 | Eng. Request for proposal | xxx - xxx - xxxxxx | 2021-01-04 | Contractor's Proposal | 1000000 | 20 | xxx - xxx - xxxxxx | 2021-01-04 | Recommended | 1000003 | Text Here | xxx - xxx - xxxxxx | 2021-01-04 | Approval with comments | 1000003 | BOQ Rate | Lump Sum | xxx - xxx - xxxxxx | 2021-01-04 | 1000000 | 20 | 2021-01-04 | Agreed | Text Here | 2021-01-04
Note on AD11: Issued : Variation has been completed and addendum has been issued to contract Agreed : Variation Approved, addendum in process Withdrawn : Proposed or instructed change cancelled Rejected : Variation has been rejected from ADM Pending Contractor : Awaiting contractor action Pending Engineer : Awaiting consultant action Pending ADM : Awaiting employer action
Note on AD22: Author: to be confirmed that a formal instruction issued

## Recap Status
Project Name : Project X
xxx - xxxxxxx- xx
Project Recap Summary
Show the status of projects recap status by completing the following table:
| Project Recap | 1750000 | Dhs
# | BOQ Section Number / Bill Number / Division Number |  | [B] BOQ RECAP Amount (AED) |  | Remarks
|  |  | Amount Submitted by the Contractor | Amount Verified by the Engineer
1 | Section Number / Bill Number / Division Number 1 |  | 100000 | 100000 | Text here
2 | Section Number / Bill Number / Division Number 2 |  | 200000 | 200000 | Text here
3 | Section Number / Bill Number / Division Number 3 |  | 300000 | 50000 | Text here
4 | Section Number / Bill Number / Division Number 4 |  | 400000 | 400000 | Text here
5 | Section Number / Bill Number / Division Number 5 |  | 500000 | 500000 | Text here
5 | Section Number / Bill Number / Division Number 6 |  | 500000 | 500000 | Text here
Section Number / Bill Number / Division Number 7

## HSE Status
Project Name : Project X
xxx - xxxxxxx- xx
PART A - OCCUPATIONAL HEALTH & SAFETY KEY PERFORMANCE INDICATORS (OHS KPIs)
# | KPIs |  | Entity | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | YTD | CPY | ITD | Q1-2021 | Q2-2021 | Q3-2021 | Q4-2021
1 | Average No. of Employees |  | Consultant | 6 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.75 | 10 | 16.75 | 6.6667 | 2.3333 | 0 | 0
|  |  | Contractor | 106 | 121 | 121 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120.25 | 200 | 320.25 | 116 | 44.3333 | 0 | 0
|  |  | Sub-Cont. | 15 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.25 | 14 | 28.25 | 14.3333 | 4.6667 | 0 | 0
|  |  | Total | 127 | 142 | 142 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.25 | 224 | 365.25 | 137 | 51.3333 | 0 | 0
2 | Man-hours worked |  | Consultant | 1248 | 1344 | 1456 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5448 | 0 | 5448 | 4048 | 1400 | 0 | 0
|  |  | Contractor | 27560 | 29040 | 32670 | 34580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123850 | 0 | 123850 | 89270 | 34580 | 0 | 0
|  |  | Sub-Cont. | 3900 | 3360 | 3780 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14680 | 0 | 14680 | 11040 | 3640 | 0 | 0
|  |  | Total | 32708 | 33744 | 37906 | 39620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143978 | 0 | 143978 | 104358 | 39620 | 0 | 0
3 | Work Days Lost |  | Consultant | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 0
4 | Reportable Incidents ( within 24 Hrs) (KPI 2-02 & KPI 3-01) | Fatality Work-Related Fatality is a death resulting from an injury or illness, regardless of the time intervening between injury and death. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reportable Serious Injury List of serious injuries that must be reported to the relevant authorities as per Schedule B (Mechanism 6.0 AD EHSMS RF). Lost time injury (LTI), Permanent total disability, Permanent partial disability, Lost workdays injury. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Reportable Occupational Illness/Disease Any work-related abnormal condition or disorder, other than an injury, which is mainly caused by exposure to environmental factors associated with the employment. | Consultant | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
|  | Reportable Dangerous Occurrence A significant incident arising out of or in the course of work that did not result in injuries and/or fatalities but had the potential to have done so. Refer to Schedule A (Mechanism 6.0 AD EHSMS RF). | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Recordable Incidents (within 24 Hrs) (KPI 2-02 , 2-06 & 3-01, 3-02) | Restricted Workday Cases (RWC) A work-related injury or illness that results in limitations on work activity that prevent an individual from doing any task of his/her normal job of from doing all of the job for any part of the day. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Medical Treatment Cases (MTC) A work-related injury or illness that calls for medication, treatment, or medical check that is administered by a health-care professional and that goes beyond first aid case. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | First Aid Injury A minor work-related injury or illness that calls for only simple “First Aid” treatment and does not call for follow-up treatment by a health-care professional. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment / Property Damage Damage to equipment or property due to an incident. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Near Misses An unplanned event, event series or condition that occurred at the workplace which, although not resulting in any injury, illness or environmental damage, had the potential to do so. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Incident Rates / Frequency | Lost Time Injury Frequency Rate (LTIFR) (KPI 2-05) The total number of Lost Time Injuries per million man hours worked during the period. LTIFR=No. of LTI's x 1,000,000/ Working Hours. | Consultant | 0 | 0 | 0 | 714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.5536 | 0 | 183.5536 | 0 | 714.2857 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 25.2398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9455 | 0 | 6.9455 | 0 | 25.2398 | 0 | 0
|  | Lost Time Injury Severity Rate (LTISR) (KPI 2-04) The total number of lost Workdays per million man hours worked during the period. LTISR=No. of Workdays Lost x 1,000,000/ Working Hours. | Consultant | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284.8752 | 0 | 1284.8752 | 0 | 5000 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 115.6738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.2971 | 0 | 32.2971 | 0 | 115.6738 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 824.1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3597 | 0 | 204.3597 | 0 | 824.1758 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 353.3569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.2371 | 0 | 97.2371 | 0 | 353.3569 | 0 | 0
|  | Total Reportable Case Frequency (TRCF) (KPI 2-03) The total reportable incidents per million man hours worked during the period. TRCF=TRC x 1,000,000/ Working Hours. | Consultant | 0 | 0 | 0 | 714.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183.5536 | 0 | 183.5536 | 0 | 714.2857 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 25.2398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9455 | 0 | 6.9455 | 0 | 25.2398 | 0 | 0
7 | EHS Department Resources (KPI 5-01) | Number of Employees in EHS Department (UAE Nationals) | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of Employees in EHS Department (Non UAE Nationals - Expatriates) | Consultant | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0
|  |  | Contractor | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 0 | 0 | 0
|  |  | Sub-Cont. | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0
|  |  | Total | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0
|  | Number of Employees attended the AD EHSMS Practitioner Course | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of Employees Registered at Qudorat | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Written warning notices from the SRA (KPI 5-04) | Number of warning notices received | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of improvement notices received | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of prohibition notices received | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Number of fines/penalties/ prosecutions received from the SRA (KPI 5-05) | Number of penalties / fines received | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Number of enforceable undertakings | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total value of all fines / penalties/ enforceable undertakings enforced (AED) | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Number of Monitoring Activities of Contractors / Supply Chain (KPI 3-03) | Review / Approval of EHS Procedures (EHS CMP Plan, Emergency Procedure, Lifting Plan, RA, EIA & Other related docs. for site work) | ADM/ DCI | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 22 | 18 | 4 | 0 | 0
|  | Inspections Performed by | ADM | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 3 | 1 | 0 | 0
|  |  | Consultant | 23 | 24 | 26 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 98 | 73 | 25 | 0 | 0
|  |  | Contractor | 35 | 43 | 45 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 166 | 123 | 43 | 0 | 0
|  | Contractor Incidents Investigated by SRA / ADM/Consultant (Entity) | SRA / ADM / Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Specific Requirement / Part System Audit | ADM/ Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Full EHSMS / IMS Audit Performed by | ADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Corrective Actions Issued by | ADM/ Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Breach Notices Issued by | ADM/ Consultant | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 3 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Permit to Work | Number of Excavation Permit issued by | Contractor | 96 | 86 | 119 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 423 | 301 | 122 | 0 | 0
|  | Number of Confined Space Permit issued by | Contractor | 75 | 78 | 110 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 366 | 0 | 366 | 263 | 103 | 0 | 0
|  | Number of Hot Work Permit issued by | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Number of Lifting Permit issued by | Contractor | 38 | 28 | 55 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 0 | 194 | 121 | 73 | 0 | 0
|  | Number of OTHER Permits issued by | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Trainings | Number of Internal Trainings | Consultant | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0 | 7 | 0 | 0
|  | Number of External (Third Party) Trainings | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0
|  | Number of HSE Induction | Consultant | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0
13 | Average Number of Training Hours per Employee (KPI 5-02) |  |  | 0 | 0 | 0 | 0.097403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10619 | 0 | 0.10619 | 0 | 0.097403 | 0 | 0
14 | Number of Tool Box Talk |  | Consultant | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 6 | 2 | 0 | 0
|  |  | Contractor | 114 | 122 | 161 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539 | 0 | 539 | 397 | 142 | 0 | 0
|  |  | Sub-Cont. | 23 | 22 | 23 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 92 | 68 | 24 | 0 | 0
|  |  | Total | 139 | 146 | 186 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 639 | 0 | 639 | 471 | 168 | 0 | 0
15 | Meetings | ADM/Consultant/Contractor |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 3 | 1 | 0 | 0
|  | Consultant/Contractor |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 3 | 1 | 0 | 0
|  | Contractor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 6 | 2 | 0 | 0
PART B-ENVIRONMENTAL KEY PERFORMANCE INDICATORS
1 | Environmental Incidents | Environment - Major An incident where irreversible or long term environmental impacts have occurred or are likely to occur to the environment and/or there is a significant health risk to workers and/or the community. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
|  | Environment - Moderate An incident where moderate reversible environmental impact has occurred or is likely to occur to the environment and/or there is a moderate health risk to workers and/or the community. | Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
|  | Environment - Minor An incident where minor, reversible damage requiring little or no remediation has occurred. For Example:Spill / Release / Discharge to Land (Including from drip tray, diesel drum, equipments) | Consultant | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub-Cont. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0
2 | Renewable Resource | Total Water Consumption (cubic meter) | Contractor | 75 | 68 | 105 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388 | 0 | 388 | 248 | 140 | 0 | 0
|  | Total Paper Consumption (Kg) | Contractor | 30 | 30 | 30 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 122 | 90 | 32 | 0 | 0
| Non-Renewable Resource | Total Power Consumption (Kilowatts Hours (kW h) ) | Contractor | 2000 | 2619 | 4477 | 8618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17714 | 0 | 17714 | 9096 | 8618 | 0 | 0
|  | Total Fuel Consumption (Litre) | Contractor | 39300 | 50670 | 64000 | 33011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186981 | 0 | 186981 | 153970 | 33011 | 0 | 0
3 | Waste Management | Non-Hazardous Waste Disposal Amount of non-hazardous (solid and liquid) waste collected by Service Providers for disposal (kg, L) | Solid (kg) by Contractor | 1000 | 150000 | 65360 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316360 | 0 | 316360 | 216360 | 100000 | 0 | 0
|  |  | Liquid (L) by Contractor | 0 | 136260 | 132490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268750 | 0 | 268750 | 268750 | 0 | 0 | 0
|  | Waste Hauling Agency (CWM approved) - Name & License No. | Fast Deer Transport CN-1175796
|  | Non-Hazardous Waste Recycling Amount of segregated non-hazardous (solid and liquid) waste collected by Service Providers for recycling / reuse / further processing (kg, L). | Solid (kg) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Liquid (L) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waste Hauling Agency (CWM approved) - Name & License No. | [15 empty] | 0 |  | 0 | 0
|  | Hazardous Waste Disposal Amount of hazardous (solid and liquid) waste collected by Service Providers for disposal (kg, L). | Solid (kg) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Liquid (L) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waste Hauling Agency (CWM approved) - Name & License No. | [15 empty] | 0 |  | 0 | 0
|  | Hazardous Waste Recycling Amount of hazardous (solid and liquid) waste collected by Service Providers for recycling / reuse / further processing (kg, L). | Solid (kg) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Liquid (L) by Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Waste Hauling Agency (CWM approved) - Name & License No.
Note on Q7: Calculation for starting current year to date
Note on R7: Calculations of Previous years
Note on S7: Calculation for starting the project to date

## HSE Training
Project Name : Project X
xxx - xxxxxxx- xx
Average No of HSE Training Hours Per Employee
|  | Consultant | Contractor | Sub-Contractor | Total Training Hours
| External Training | 0 | 0 | 16 | 16 | Avg. No of Employees |  | 5
| Internal Training | 24 | 35 | 0 | 59 | Avg.No of training hours per Employee |  | 18.2
| Induction | 16 | 0 | 0 | 16 |  |  | Hours
| Total Training Hours | 40 | 35 | 16 | 91
| Type of EHS Training | Entity | Number of Sessions | Training Date | Training Topic | Period in Hours | No. of Attendees | Total Training Hours
| Induction | Consultant | 6 | 2021-04-08 | Text Here | 2 | 8 | 16
| Internal Training | Consultant | 2 | 2021-04-09 | Text Here | 3 | 8 | 24
| External Training | Sub-Contractor | 2 | 2021-04-10 | Text Here | 2 | 8 | 16
| Internal Training | Contractor | 5 | 2021-04-11 | Text Here | 7 | 5 | 35
| Induction | Sub-Contractor
Note on H8: Avg. No of Employees for the Project during the reporting period

## HSE Incidents
Project Name : Project X
xxx - xxxxxxx- xx
Project Incidents Details
Incident Category | Entity | Contract No: | Incident |  |  |  | Injuries | [7 empty] | Activity Type | Incident Photo
|  |  | Incident Location | Incident Date | Incident Time | Description of Incident (Brief description within 5 sentences) | Age | Nationality | Job Title | Experience | Injured person | Name of the Injured Person's Organisation | Body part injured/ Property damage/ | Work Days Lost
Env.Minor | Consultant | O-12727 | W-16 | 2021-04-05 | 10.30 am | Auger drill accidentally hit the nearby existing Sewer force main line (250mm Dia GRP of Pumping Station - PS3/7) and subsequent damages resulted in minor sewer discharge on the ground. | N/A | N/A | N/A | N/A | Sub-Contractor | N/A | N/A | 2 | Geo-Technical Soil Investigation
Env.Major | Sub-Contractor | O-12728 | W-17 | 2021-04-06 | 10.30 am | Auger drill accidentally hit the nearby existing Sewer force main line (250mm Dia GRP of Pumping Station - PS3/7) and subsequent damages resulted in minor sewer discharge on the ground. | N/A | N/A | N/A | N/A | Sub-Contractor | N/A | N/A | 3 | Geo-Technical Soil Investigation
Env.Medium | Contractor | O-12729 | W-18 | 2021-04-07 | 10.30 am | Auger drill accidentally hit the nearby existing Sewer force main line (250mm Dia GRP of Pumping Station - PS3/7) and subsequent damages resulted in minor sewer discharge on the ground. | N/A | N/A | N/A | N/A | Sub-Contractor | N/A | N/A | 4 | Geo-Technical Soil Investigation
Occupational Illness | Consultant | O-12730 | W-19 | 2021-04-08 | 10.30 am | Auger drill accidentally hit the nearby existing Sewer force main line (250mm Dia GRP of Pumping Station - PS3/7) and subsequent damages resulted in minor sewer discharge on the ground. | N/A | N/A | N/A | N/A | Sub-Contractor | N/A | N/A | 5 | Geo-Technical Soil Investigation
First Aid Injury
Property Damage

## HSE NCR Log
Project Name : Project X
xxx - xxxxxxx- xx
HSE NCR REGISTER
# | Report No. | Description | Serverity | Date Open | Date Close | Status | Days Pending | Reported By | Remarks
1 | DCIL-EHS-NCR-C-1-CCC-001 | Excavation without safety arrangements, proper detour/traffic management, plastic barriers not secured, PPE | High | 2018-10-20 | 2018-10-27 | Pending | 5 | Name Here